Sprint Backlog

SCRUM master: Ido Rotner

Product owner: Yohad ben baruch

Team: Ido Rotner id: 322465279 mail: Ido.rotner@e.braude.ac.il

Liel Etinger  id: 207411604 mail: Liel.Etinger@e.braude.ac.il

Yohad ben Baruch id: 211624317 mail: Yohad.Ben.Baruch@e.braude.ac.il

Ester Peretz id: 318739117 mail: Ester.Peretz@e.braude.ac.il

|  | Previous activity | end date | Responsible | Planned % Completion | Duration (Hours) | start date | Activity description | Activity ID |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 |  |  |  |  |  |  |  |  |
| week 1 Functional Requirements | - | 26/10 | Yohad | 99% | 2 | 26/10 | Collect project story and assignment requirements | 1 |
|  | 1 | 27/10 | Ido | 99% | 2 | 27/10 | Development environment preparation (Eclipse, VP 17.2, Git, ToDoList, shared repo) | 2 |
|  | 1 | 28/10 | Yohad | 90% | 2 | 27/10 | Analyze and detail Functional Requirements | 3 |
|  | 3 | 29/10 | Ester | 70% | 2 | 29/10 | Analyze and detail non Functional Requirements | 4 |
|  | 4 | 30/10 | Ester | 99% | 1 | 30/10 | Build Functional Requirements in Excel | 5 |
|  | 5 | 31/10 | Liel | 99% | 0.10 | 31/10 | Daliy Scram: : Finalize & Submission Prep (Collect deliverables) | 6 |
|  | 5 | 31/10 | Liel | 90% | 1 | 31/10 | use-case material refreshment | 7 |
| week 2 Use-Case Acceptance Test | 7 | 3/11 | Ester | 99% | 2 | 1/11 | Build Use Case diagram (in Visual Paradigm) including identifying and defining all Actor and scenarios | 8 |
|  | 8 | 4/11 | Liel | 80% | 2 | 4/11 | Write detailed Use Case description, focusing on the Data Flow/Flow of Events (Main Scenario) | 9 |
|  | 9 | 5/11 | Ido | 75% | 3 | 5/11 | Define Acceptance Criteria & Test Cases document (Excel) | 10 |
|  | 10 | 6/11 | Liel | 60% | 2 | 6/11 | Write test cases for reservation | 11 |
|  | 10 | 6/11 | Ido | 70% | 2 | 6/11 | Write test cases for getting & freeing table | 12 |
|  | 11,12 | 7/11 | Ester | 99% | 2 | 7/11 | GitHub public repository setup (finalizing folders for Assignment 1) | 13 |
|  | 13 | 8/11 | Yohad | 90% |  | 8/11 | Milestone: End Assignment 1. | 14 |
|  | 13 | 8/11 | Ester | 90% | 0.10 | 8/11 | Daliy Scram: Submission 1 Prep (Collect Assignment 1 deliverables) | 15 |
| Sprint 2 product Log |  |  |  |  |  |  |  |  |
| week 3 Activity | 15 | 8/11 | Yohad | 90% | 2 | 8/11 | Study Activity diagram | 16 |
|  | 16 | 11/11 | Liel | 95% | 3 | 9/11 | Build Activity Diagram for reservation | 17 |
|  | 16 | 11/11 | Ester | 99% | 2 | 9/11 | Build Activity Diagram for Manager Reports for subscriber client | 18 |
|  | 11,12,17,18 5,8 | 14/11 | Liel | 80% | 1 | 12/11 | Fixing and Review the diagrams | 19 |
|  | 19 | 15/11 | Ido | 99% | 0.10 | 15/11 | Daliy Scram: Diagrams Prep (Collect diagrams). | 20 |
| week 4 Sequence | 20 | 17/11 | Ido | 80% | 2 | 16/11 | Sequence diagram material refreshment | 21 |
|  | 21 | 19/11 | Ester | 70% | 3 | 18/11 | Identify actors and life line for Manager Reports for subscriber client | 22 |
|  | 21 | 19/11 | Liel | 80% | 2 | 18/11 | Identify actors and life line for reservation client | 23 |
|  | 22,23 | 20/11 | Ido | 90% | 2 | 20/11 | Find the connections between the life line for each sequence | 24 |
|  | 22,23,24 | 21/11 | Yohad | 99% | 2 | 21/11 | Build final sequence in VP and validate against requirements | 25 |
|  | 25 | 22/11 | Yohad | 99% | 1 | 22/11 | Daliy Scram: sequence Prep (Collect sequence | 26 |
| week 5 | 26 | 25/11 | Ester | 80% | 1 | 23/11 | Class diagram material refreshment | 27 |
|  | 27 | 27/11 | Yohad | 70% | 3 | 26/11 | Define key methods and interfaces for classes | 28 |
|  | 28 | 27/11 | Ester | 99% | 1 | 26/11 | Identify the Screens GUI | 29 |
|  | 28 | 29/11 | Liel | 70% | 2 | 28/11 | Add External Connections Ocsf/jdbc | 30 |
|  | 27,28,29,30 | 30/11 | Yohad | 70% | 1 | 30/11 | Build final Class Diagram in VP | 31 |
|  | 31 | 1/12 | Ester | 99% | 1 | 1/12 | Milestone: Finishing the Diagrams Complete. | 32 |
|  | 32 | 1/12 | Liel | 99% | 0.10 | 1/12 | Daliy Scram: Class Diagram Prep | 33 |
| week 6 | 33 | 2/12 | Liel | 90% | 2 | 2/12 | Refreshment of JavaFX GUI material and Java | 34 |
|  | 34 | 2/12 | Ester | 99% | 1 | 2/12 | Build the order screen design | 35 |
|  | 34 | 4/12 | Yohad | 99% | 1 | 3/12 | Set up the Database connection and confirm it works. | 36 |
|  | 36 | 5/12 | Ido | 90% | 3 | 5/12 | Build the main server functions For the order (like saving and loading data). | 37 |
|  | 35,37,36 | 6/12 | Ester | 90% | 3 | 6/12 | Connect GUI components to server-side logic and verify data flow. | 38 |
|  | 38 | 6/12 | Ido | 99% | 0.10 | 6/12 | Daliy Scram: Final Prep (Collect GUI deliverables and prepare for submission.) | 39 |
|  | 39 | 7/12 | Liel | 95% |  | 7/12 | Milestone: End Assignment 2. | 40 |

ניהול פרוייקט חלק ראשון משופר

|  | Previous activity | end date | Responsible | Planned % Completion | Duration (Hours) | start date | Activity description | Activity ID |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| week 1 Functional Requirements | - | 26/10 | Yohad | 99% | 2 | 26/10 | Collect project story and assignment requirements | 1 |
|  | 1 | 27/10 | Ido | 99% | 2 | 27/10 | Development environment preparation (Eclipse, VP 17.2, Git, ToDoList, shared repo) | 2 |
|  | 1 | 28/10 | Yohad | 90% | 2 | 27/10 | Analyze and detail Functional Requirements | 3 |
|  | 3 | 29/10 | Ester | 70% | 2 | 29/10 | Analyze and detail non Functional Requirements | 4 |
|  | 4 | 30/10 | Ester | 99% | 1 | 30/10 | Build Functional Requirements in Excel | 5 |
| week 2 Use-Case Acceptance Test | 5 | 31/10 | Liel | 90% | 1 | 31/10 | use-case material refreshment | 6 |
|  | 6 | 3/11 | Ester | 99% | 2 | 1/11 | Build Use Case diagram (in Visual Paradigm) including identifying and defining all Actor and scenarios | 7 |
|  | 7 | 4/11 | Liel | 80% | 2 | 4/11 | Write detailed Use Case description, focusing on the Data Flow/Flow of Events (Main Scenario) | 8 |
|  | 8 | 5/11 | Ido | 75% | 3 | 5/11 | Define Acceptance Criteria & Test Cases document (Excel) | 9 |
|  | 9 | 6/11 | Liel | 60% | 2 | 6/11 | Write test cases for reservation | 10 |
|  | 9 | 6/11 | Ido | 70% | 2 | 6/11 | Write test cases for getting & freeing table | 11 |
|  | 10,11 | 7/11 | Ester | 99% | 2 | 7/11 | GitHub public repository setup (finalizing folders for Assignment 1) | 12 |
|  | 12 | 8/11 | Yohad | 90% |  | 8/11 | Milestone: End Assignment 1. | 13 |
| week 3 Activity | 13 | 8/11 | Yohad | 90% | 2 | 8/11 | Study Activity diagram | 14 |
|  | 14 | 11/11 | Liel | 95% | 3 | 9/11 | Build Activity Diagram for reservation | 15 |
|  | 15 | 11/11 | Ester | 99% | 2 | 9/11 | Build Activity Diagram for Manager Reports for subscriber client | 16 |
|  | 15,10, 11 5,8 | 14/11 | Liel | 80% | 1 | 12/11 | Fixing and Review the diagrams | 17 |
| week 4 Sequence | 17 | 17/11 | Ido | 80% | 2 | 16/11 | Sequence diagram material refreshment | 18 |
|  | 18 | 19/11 | Ester | 70% | 3 | 18/11 | Identify actors and life line for Manager Reports for subscriber client | 19 |
|  | 18 | 19/11 | Liel | 80% | 2 | 18/11 | Identify actors and life line for reservation client | 20 |
|  | 19,20 | 21/11 | Ido | 90% | 2 | 20/11 | Find the connections between the life line for each sequence | 21 |
|  | 19,20,21 | 22/11 | Yohad | 99% | 2 | 22/11 | Build final sequence in VP and validate against requirements | 22 |